## Reduced CRISP-DM Methodology
Program Code | Project Code | WBS Identifier and Level | Q-Gate/Criteria/Deliverable Name | Sign-off Checklist? Use Green or Red fill
MDS 560 Spring 2019 | Bank Project | 1 | Phase 1 Business Understanding | Yes
MDS 560 Spring 2019 | Bank Project | 1.1 | Create a Project Charter using the template provided in your PRIMMS document repository. Identify the current rate of churn experienced by the bank and assess (roughly) the potential savings by the bank in reducing this churn by 25% as an objective. We assume that rate of customer churn is a critical KPI for the bank. | Yes
MDS 560 Spring 2019 | Bank Project | 1.2 | Develop preliminary model (prototype) using Automodel on your training dataset and assess performance. Do the results support show adequate performance to support the business case and justify moving forward with the project? | Yes
MDS 560 Spring 2019 | Bank Project | 2 | Phase 2 Data Access and Understanding | Yes/No
MDS 560 Spring 2019 | Bank Project | 2.1 | Load your full training dataset in Rapidminer | Yes
MDS 560 Spring 2019 | Bank Project | 2.2 | Explore your training data looking for unusal distributions, missing values and obvious errors | Yes
MDS 560 Spring 2019 | Bank Project | 2.3 | Make adjustments as appropriate in data | Yes
MDS 560 Spring 2019 | Bank Project | 2.4 | Verify Data Quality | Yes
MDS 560 Spring 2019 | Bank Project | 3 | Phase 3 Data Preparation Phase | Yes
MDS 560 Spring 2019 | Bank Project | 3.1 | Re-run the model and identify any possible outliers | Yes
MDS 560 Spring 2019 | Bank Project | 3.2 | Re-run the model and identify any weak or potential redundant predictor variables. Remove those variables from your models. | Yes
MDS 560 Spring 2019 | Bank Project | 3.3 | Consider feature engineering that may be appropriate and (if appropriate) create new variables using Turbo Prep and add those variables to the models. | Yes
MDS 560 Spring 2020 | Bank Project | 3.4 | Consider any imbalances in your dataset that may require any adjustments in sampling. | Yes
MDS 560 Spring 2021 | Bank Project | 3.5 | Consider what classification threshold value would be appropriate if using logistic regression. | Yes
MDS 560 Spring 2019 | Bank Project | 4 | Phase 4 Modeling Phase | Yes
MDS 560 Spring 2019 | Bank Project | 4.1 | Evaluate the performance of all available modeling engines provided in Rapidminer Automodel using the dataset produced from phase 3 above. | Yes
MDS 560 Spring 2019 | Bank Project | 4.2 | Select the single best performing modeling engine and evaluate hyper-parameter settings as appropriate. Your criteria for modeling engine selection should consider precision as highest priority, recall as secondary priority and accuracy as third priority. No machine learning engine should be considered that produces an AUC less than 0.60. | Yes
MDS 560 Spring 2020 | Bank Project | 4.3 | Iterate the model as appropriate to optimize your model in order to meet the business objectives. | Yes
MDS 560 Spring 2019 | Bank Project | 4.4 | Apply the "best" model to the production dataset and produce forecasted labels to each record. | Yes
MDS 560 Spring 2020 | Bank Project | 4.5 | Sort the production dataset in descending order of probability of churn. Using customer number Identify the top 100 customers in the production dataset who are most likely to churn. Provide a recommended short-term course of action for the bank that could lead to the bank retaining these customers. | Yes
MDS 560 Spring 2019 | Bank Project | 4.6 | Summarize your findings indicating which variables appear to be most important in influencing customer churn for the bank. | Yes/No
MDS 560 Spring 2019 | Bank Project | 4.7 | Given your understanding of the variables that influence churn, summarize your recommended actions that the bank should consider taking over the longer term in order to reduce customer churn by the target 25%. | Yes/No
MDS 560 Spring 2020 | Bank Project | 4.8 | Construct a "profile" of the customers who are most likely to churn. Include this profile as justification to support your recommendation for action by the bank. | Yes/No
MDS 560 Spring 2021 | Bank Project | 4.9 | Using a Clustering method (segmentation )of your choice within Rapidminer, identify the major market segments and consider these segments as part of your recommendation to the bank. | Yes/No
MDS 560 Spring 2020 | Bank Project | 4.10 | Assuming that the bank has multiple locations throughout Europe, describe options of how the bank might deploy this machine learning model to users at each of these locations. | Yes/No
MDS 560 Spring 2020 | Bank Project | 4.11 | Close Out the project by "signing off" to all steps in the checklist provided in column E of this spreadsheet. Ensure that your powerpoint presentation covers each item of the checklist. | Yes