## ProjectOverview
Program Code | Project Code | Identifier and Level | Q-Gate/Criteria/Deliverable Name | Planned start date | Planned Finish Date | Percent complete | Actual Start Date | Actual Finish Date | Responsible
MDS 560 SPRG 20 | Cusey | 1 | Phase 1 Business Understanding | 2020-03-30 | 2020-04-12 | 0
MDS 560 SPRG 20 | Cusey | 1.1 | Determine Business Objectives | 2020-03-30 | 2020-04-10 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 1.1.1 | Interview stakeholders and create first draft value map | 2020-03-30 | 2020-04-10 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 1.1.2 | First draft requirements document completed | 2020-03-30 | 2020-04-10 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 1.1.3 | Team meeting with sponsor completed to clarify objectives and roles. | 2020-03-30 | 2020-04-10 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 1.2 | assess the situation | 2020-03-30 | 2020-04-11 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 1.2.1 | Inventory resources requirements assumptions and constraints | 2020-03-30 | 2020-04-11 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 1.2.2 | Identify risks and contingencies | 2020-03-30 | 2020-04-11 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 1.2.3 | Develop preliminary model (prototype) and determine value props and ROI for Continuing project. | 2020-03-30 | 2020-04-11 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 1.3 | Determine Data Mining Goals | 2020-03-30 | 2020-04-11 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 1.3.1 | Assess the need to continue going further and if so, identify data mining-data science goals | 2020-03-30 | 2020-04-11 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 1.3.2 | Determine if rough working model is adequate to meet the process needs. | 2020-03-30 | 2020-04-11 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 1.4 | Project Management | 2020-03-30 | 2020-04-12 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 1.4.1 | Team Create Project Charter and Sponsor Signs off | 2020-03-30 | 2020-04-12 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 1.4.2 | Create Project Plan | 2020-03-30 | 2020-04-12 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 1.4.3 | Business Case Documented and Justifies Project Going Forward | 2020-03-30 | 2020-04-12 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 1.4.4 | Resources are assigned and available | 2020-03-30 | 2020-04-12 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 2 | Phase 2 Data Access and Understanding | 2020-04-13 | 2020-04-19 | 0
MDS 560 SPRG 20 | Cusey | 2.1 | Access and collect initial data | 2020-04-13 | 2020-04-15 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 2.1.1 | Databases | 2020-04-13 | 2020-04-15 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 2.1.2 | Sensors | 2020-04-13 | 2020-04-15 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 2.1.3 | Files | 2020-04-13 | 2020-04-15 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 2.1.4 | Initial data report -Develop a model using existing data and determine model strength as measured by a measure of goodness of fit. | 2020-04-13 | 2020-04-15 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 2.2 | Describe data | 2020-04-13 | 2020-04-18 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 2.2.1 | Data description report | 2020-04-13 | 2020-04-18 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 2.3 | Explore Data | 2020-04-13 | 2020-04-16 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 2.3.1 | Business and Transactional Data: Repositories, File I/O, and web sources | 2020-04-13 | 2020-04-16 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 2.3.2 | Data Exploration identifies all potentially relevant in-house data . | 2020-04-13 | 2020-04-16 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 2.4 | Verify Data Quality | 2020-04-13 | 2020-04-17 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 2.4.1 | Data Quality Report: Identify data gaps and determine feasibility of acquiring the needed data. | 2020-04-13 | 2020-04-17 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 2.4.2 | Requirements Document updated based upon prototype evaluation and user feedback | 2020-04-13 | 2020-04-17 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 2.4.3 | Data Quality Report: Determine if existing data will provide adequate AUC | 2020-04-13 | 2020-04-17 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 2.5 | Develop System Prototype in Dev Environment | 2020-04-13 | 2020-04-19 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 2.5.1 | Review and assess prototype. Create and Validate Requirements Document | 2020-04-13 | 2020-04-19 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 2.5.2 | Identify data gaps and develop strategy for obtaining needed data. | 2020-04-13 | 2020-04-19 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 2.5.3 | Complete first iteration of Build-Test cycle resulting in an objective assessment of existing data capability | 2020-04-13 | 2020-04-19 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 3 | Phase 3 Data Preparation Phase | 2020-04-20 | 2020-04-26 | 0
MDS 560 SPRG 20 | Cusey | 3.1 | Enhanced Prototype and System Walkthrough Completed | 2020-04-21 | 2020-04-26 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 3.1.1 | System Walkthrough Completed | 2020-04-21 | 2020-04-26 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 3.1.2 | All critical issues resolved | 2020-04-21 | 2020-04-26 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 3.2 | Describe Data | 2020-04-20 | 2020-04-25 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 3.2.1 | Data dictionary completed. | 2020-04-20 | 2020-04-25 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 3.3 | Select Data | 2020-04-20 | 2020-04-22 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 3.3.1 | ETL design completed and documented. | 2020-04-20 | 2020-04-22 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 3.3.2 | Required Data Fields identified and under change control | 2020-04-20 | 2020-04-22 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 3.4 | Clean and Aggregate Data | 2020-04-20 | 2020-04-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 3.4.1 | Different Sources --files, web, etc | 2020-04-20 | 2020-04-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 3.4.2 | Different Types--images, text , flat files, etc. | 2020-04-20 | 2020-04-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 3.4.3 | Data are cleaned and harmonized following appropriate business rules | 2020-04-20 | 2020-04-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 3.5 | Construct Data | 2020-04-20 | 2020-04-23 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 3.5.1 | Perform Feature Engineering as Appropriate and Construct All Variables | 2020-04-20 | 2020-04-23 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 3.6 | Integrate Data and Dealing with Out of Memory Data (Big Data) | 2020-04-20 | 2020-04-25 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 3.6.1 | Data from various source systems is successfully combined for loading into machine learning or time series applications. | 2020-04-20 | 2020-04-25 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 3.7 | Format the data and handle domain specific processing issues | 2020-04-20 | 2020-04-25 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 3.7.1 | All formatting issues are resolved. Data successfully loaded into prototype 2 QA environment | 2020-04-20 | 2020-04-25 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4 | Phase 4 Modeling Phase | 2020-04-27 | 2020-05-10 | 0
MDS 560 SPRG 20 | Cusey | 4.1 | Working with Messy Data | 2020-04-27 | 2020-05-01 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.1.1 | Handling Problems of missing values, differing time intervals, etc | 2020-04-27 | 2020-05-01 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.2 | Develop Iteration 2 prototype and System Test in QA Environment | 2020-04-27 | 2020-05-10 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.2.1 | Walkthrough 2 completed all critical and high issues resolved | 2020-04-27 | 2020-05-10 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.2.2 | 1) Develop-test-assess Iteration 2 prototype in Dev and Promote to a QA Environment for user acceptance testing 2) Resolve all key issues and problems. | 2020-04-27 | 2020-05-10 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.3 | Select Modeling Technique | 2020-04-27 | 2020-05-04 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.4 | Select Modeling and Analytical Tools | 2020-04-27 | 2020-05-02 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.4.1 | Evaluate and Test an adequately robust suite of tools for modeling. Select best option. | 2020-04-27 | 2020-05-02 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.5 | Generate Test Design | 2020-04-27 | 2020-05-05 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.5.1 | Report on the design | 2020-04-27 | 2020-05-05 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.6 | Build model parameter settings | 2020-04-27 | 2020-05-08 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.6.1 | Set baseline model and place under change control | 2020-04-27 | 2020-05-08 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.3.1 | 1) Test model robustness using all available tools and techniques 2) Try multiple models and select best performing model and put under change control | 2020-04-27 | 2020-05-04 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.7 | Assess the model | 2020-04-27 | 2020-05-07 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.7.1 | AUC >= 0.80 using 20 fold validation if machine learning is employed | 2020-04-27 | 2020-05-07 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.8 | Data Reduction and Transformation | 2020-04-27 | 2020-05-03 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.8.1 | How to transform the data to best represent the system | 2020-04-27 | 2020-05-03 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.9 | Feature Selection and Extraction | 2020-04-27 | 2020-05-04 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.9.1 | Feature selection--what attributes or what subsets of data to use | 2020-04-27 | 2020-05-04 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 4.9.2 | Freature engineering--creating new attributes that improve model usefullness and performance | 2020-04-27 | 2020-05-04 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 5 | Phase 5 Evaluation Phase | 2020-05-11 | 2020-05-17 | 0
MDS 560 SPRG 20 | Cusey | 5.1 | Evaluate Results and Validate Readiness for Deployment | 2020-05-11 | 2020-05-17 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 5.1.1 | Align assessment of data mining results with business success criteria- Provide report- | 2020-05-11 | 2020-05-17 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 5.2 | Review the model and process | 2020-05-11 | 2020-05-17 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 5.2.1 | Report on Approval Sign off on models and process | 2020-05-11 | 2020-05-17 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 5.3 | Develop and deliver training to users | 2020-05-11 | 2020-05-17 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 5.3.1 | Develop and deliver training to users | 2020-05-11 | 2020-05-17 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 5.3.2 | Create list of decisions | 2020-05-11 | 2020-05-17 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 5.3.3 | Validate value propositions | 2020-05-11 | 2020-05-17 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 5.3.4 | Create List of possible actions | 2020-05-11 | 2020-05-17 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 5.4 | Integration Testing and User Acceptance Testing Completed | 2020-05-11 | 2020-05-16 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 5.4.1 | SIT and UAT Tests Executed Successfully | 2020-05-11 | 2020-05-16 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 5.4.2 | All critical, high and medium defects resolved | 2020-05-11 | 2020-05-16 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 5.4.3 | Test Cases Created | 2020-05-11 | 2020-05-16 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 6 | Phase 6 Deployment Phase | 2020-05-18 | 2020-05-31 | 0
MDS 560 SPRG 20 | Cusey | 6.1 | Plan Deployment | 2020-05-18 | 2020-05-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 6.1.1 | Update project plan to cutover and include deployment activities | 2020-05-18 | 2020-05-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 6.2 | Plan monitoring/ maintenance and attainment of value propositions | 2020-05-18 | 2020-05-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 6.2.1 | Update project plan to include monitoring and maintenance activities | 2020-05-18 | 2020-05-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 6.2.2 | Update plan to drive value propositions to realization | 2020-05-18 | 2020-05-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 6.3 | Produce final report | 2020-05-18 | 2020-05-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 6.3.1 | Submit final report | 2020-05-18 | 2020-05-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 6.4 | Review Project | 2020-05-18 | 2020-05-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 6.4.1 | Lessons learned | 2020-05-18 | 2020-05-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 6.4.2 | document the experience | 2020-05-18 | 2020-05-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 6.4.3 | close out project deliverables | 2020-05-18 | 2020-05-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 6.4.4 | archive project artifacts | 2020-05-18 | 2020-05-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 6.4.5 | deliver presentation and begin project execution | 2020-05-18 | 2020-05-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 6.5 | Integrate analytics with systems--Go Live and stabilize | 2020-05-18 | 2020-05-31 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 6.5.1 | Load and Validate Data in PRD-embedded hardware or enterprise systems | 2020-05-18 | 2020-05-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 6.5.2 | Deploy Model to PRD--embedded hardware or enterprise systems | 2020-05-18 | 2020-05-24 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 6.5.3 | Stabilization complete | 2020-05-18 | 2020-05-31 | 0 |  |  | Student
MDS 560 SPRG 20 | Cusey | 6.5.4 | Value attainment starts measurement-begin monitoring, measure KPIs and drive value | 2020-05-18 | 2020-05-31 | 0 |  |  | Student